## Slide 1: Performance Team activities
Jun 18, 2024

## Slide 2: Scope of LMR
LMR –
  Understanding the Performance testing scope for LMR
  Confirm the NFR numbers from the E2E application for the LMR release and document
  Understanding the workflow and architecture related to LMR release
  Preparing Performance Test Plan
  JMeter PoC, building report generation script, execution and ensuring to achieve defined TPS
  Work with DevOps, Cloud to provision the Performance Environment to support LMR
  Building process and follow up with teams to get the test data injected to Perf environment to support LMR
  Building report generation script (1)
  Execution of dry run
  Monitor the ETL process
  For DV, setting up test data, execution of dry run, ETL process
FMR –
List of scope

## Slide 3: Scope of FMR
FMR –
  Understanding the Performance testing scope for FMR. Need to go through 4 features and understand them in detail
  Understanding the Performance testing scope for benchmarking for FMR. Need to go through 4 features and understand them in detail
  Confirm the NFR numbers from the E2E application for the FMR release and document
  Understanding the workflow and architecture related to FMR release
  Preparing Performance Test Plan
  Azure DevOps Pipeline setup for JMeter
  JMeter PoC from Azure DevOps, building report generation script, execution and ensuring to achieve defined TPS
  Building process and follow up with teams to get the test data injected to Perf environment to support FMR
  Building report generation script (6+), execution of dry run and ensuring the readiness
  Execution of actual test
  Monitor the ETL process
  Support or follow up on the benchmarking executions with the BE team
  For on-demand and ETL execution phase, update JMeter scripts, test data setup, executions and reporting
  Post 1.5 code base deployment, verification of the functionalities
  DV, setting up test data, execution of dry run, ETL process
List of scope

## Slide 4: LMR - Activities status wise
Sl. No | Activities | Status
1 | Attended the calls with Teresa, Leo, Alli and understood the LMR requirements and work load model | Completed
2 | Prepared the LMR Test plan, reviewed and closed | Completed
3 | Updated the “Resource requirements confluence page” for LMR | Completed
4 | Prepared the JMeter script for report generation to meet the LMR expectations | Completed
5 | For JMeter PoC, executed multiple rounds of tests to meet the LMR expectations of 3.8 or 4 TPS, with 0 (zero) errors. | Completed
6 | Followed up on E2E support for Discovery requirement and closed. Updated confluence page. | Completed
7 | Worked with DevOps team on getting the Performance environment. | Completed
8 | Requested and got the respective access for Azure DevOps Performance environment for monitoring purpose. | Completed
9 | Regularly updated the assigned Jira’s also raised new Jira’s based on the needs. | Completed
10 | Follow-up with team to run the load injector scripts in Perf environment | In-Progress. Sprit#5 (June 5 to 18)
11 | Follow-up with team on injected to the data load for the loaded CIDs | In-Progress. Sprit#5 (June 5 to 18)
12 | Follow-up with cloud team on getting the confirmation on the cloud environment and load the 90 days data for the same CIDs | In-Progress. Sprit#5 (June 5 to 18)
13 | Migrate the qa script to Perf environment script. Update the test data and perform a dry run to ensure the script and environment readiness | Completed
14 | Execute the dry run report generation test, monitor the test and prepare high level report. | In-Progress. Sprit#5 (June 5 to 18)
15 | Monitor the ETL pull for 5 min once the data is loaded, monitor and report | In-Progress. Sprit#6 (June 19 to July 2nd )

## Slide 5: FMR - Activities status wise
Sl. No | Activities | Status
1 | Understanding of 4 features for FMR and 4 benchmarking features | In-Progress
2 | Prepared the E2E support needs for discover confluence page is updated with both LMR and FMR numbers. Updated the same on Teresa review comments. | In-Progress
3 | Sent an email to E2E team to provide the FMR numbers. | In-Progress
4 | Updated the resource planning needs confluence page based on the sprint wise. This needs to be still updated based on the understanding and planning. | In-Progress
5 | Build Performance Test plan – drafting of the plan has started | In-Progress
6 | For each feature, based on the understanding need to raise the respective tasks, identify the support team, do estimations etc., | In-Progress
7 | Schedule calls / connect over emails / group chats with Cloud, DevOps, and Eng. teams | In-Progress
8 | Schedule regular calls, send emails to respective teams based on the needs to get the things going | In-Progress
FMR sprints starting from 10th July to 1st Oct
As this is the planning phase, below are the list of activities which are identified based on the discussions and confirmation. As we progress, we should be getting more activities, user stories.

## Slide 6: Concerns
There are no concerns on the LMR, we are on-track and likely to finish as per the sprint planning.
Based on the FMR features, we need more understanding on the architecture, technical details in collaboration with process wise. This would help us to build the proper strategy for Performance Testing
Also, need to understand the in-scope scenarios as it will help us to estimate on building the test scripts, setting up the test data, dry run executions etc.,
I see that and discussed with Leo that building JMeter scripts with handling the bearer token which has an expiry time of 1hr. As in FMR, we shall be using more number of users, we should use java code to generate or maintain the same bearer token or authentication for proper execution of the test. For that we need a good technical person to build the robost scripts
I understand most of the teams are working in CST hours and I being working in IST, this is hard to catch-up with our / support teams to be in sync.
Being on 1.5 months old in the system, needs some more time to see things practically rather than theoretically.
List of concerns

## Slide 7: Thank you!