## Slide 1: Performance Test Plan for 1.5 FMR Release (API Only) – Q1’2025
15th Jan 2025

## Slide 2
Objective & Feature Details for Q1’2025
Architecture Diagram
Dependencies
Pre-requisites and Tools
NFRs and In-scope Scenarios
Volume Details (API & ETL)
Overall Execution Summary for API only
API Goals
  Goal#1 – All in-scope Scenario include report generation (HCP)
  Goal#2 – Stress & Endurance Test (All In-scope scenarios)
List of Functionalities and Out Of Scope
PT Environment Details
Table of Contents

## Slide 3
Objective:
For FMR release execute the below agreed Load tests for HCP and PwD scenarios to understand the overall systems behavior, stability and responsiveness of the API & GUI performance for an application. Also, ensure that per NFR requirements, all the in-scope scenarios for HCP and PwD meet the targeted SLAs, server health is within the threshold limit
1.5 FMR In-scope List of Features:
Objective & Feature Details for Q1’2025
Feature Number | Year & Quarter | Type of Feature | Description | Status
INSIGHT-776 | 2025 & Q1 | API Only | Performance team will discover all the identified workflows (Navigations, search, invitations, report gen) and prepare API scripts in the available PF environment FMR 1.5 Release Performance Test for Discover HCP & PwD - API Only | In-Progress
INSIGHT-738 | 2025 & Q1 | API Only | Perf Test: API Performance Testing on 1.5 code in Perf test with 1.6 numbers (including report generation and hybrid cloud ETL) | To-Do
INSIGHT-736 | 2025 & Q1 | API | All in-scope scenario API scripts to be migrated to PF2 environment (DV Testing), perform validations, identify test data needs for scripting and execution. Design test scenarios and perform dry run or sanity checks. | To-Do

## Slide 4
Architecture Diagram

## Slide 5
Dependencies
Sl. No. | Dependency | Owner | Comments
1 | PF & PF2 environment availability | Alejandro Duran Orozco | Stable environment, test data to be available with OQ and IQ process complete
2 | ETL Services and Insights Services | Ramses García Duran | ETL and Insights services to be working.
2 | API mock okta setup in PF | Aline Thomé Williams | Mock okta to be deployed in PF. Perf team to perform sanity check with all in-scope scenarios to ensure the readiness
3 | GUI Mock Okta setup in PF | Daniel Vital Sánchez | Mock okta to be deployed in PF. Perf team to perform sanity check with all in-scope scenarios to ensure the readiness
4 | User Creation for HCP & PwD applications | Alli Przybylowicz | All required active login users to be created with help of E2E team
5 | MFA Disable for all the users | Arturo Garcia Martinez | With help of Arturo, all active users to be added to the group to skip the MFA
6 | 1.5 latest code along with Hybrid pull availability | Eduardo Portal Geroy | Dev team to close the development as the report generation is dependent on the hybrid pull feature.
7 | Code deployment | Eduardo Miranda Ramirez | Team to help or shadow Perf team on latest code deployment into PF. Perf team to perform OQ to ensure the environment, application readiness
8 | Historical data for 90 days and 2 weeks of futuristic data to be loaded to PF | Laura Zacherl | Team to load the required data into PF
9 | Issue / Bug fixes in PF | Andrew Zheng | Dependency on Dev team to provide the fixes, optimize for the identified issues from the executions. So, that Perf team can re-execute or unblock from continuing from next planned executions
10 | Server-side Monitoring | Mohammad Islam | Optional, Datadog setup for monitoring the server-side metrics
11 | Data model | Teresa Janz | Data model for all in-scope scenarios to be completed, finalize the numbers to start with the execution
12 | SRS creation or finalization | Marshall Bernklow | Confirm if SRS to be created, provide metrics to compare with the actual results

## Slide 6
Pre-requisites and Tools
As part of 1.5 FMR release activities, the below activities needs to completed in order to start performance testing activities
Ensure that 1.5 code is being deployed into Performance environment
  Okta to be mocked in Performance environment
  OQ process is completed
  List all the new functionalities which are being deployed and available for testing
Per WLM with addition of buffer on the volume. Following users to be created in the system before start of the executions.
  Please refer to section 1.3 1.5 Volumes for the volume details
Below steps to be followed to load 50,000 PWD
  1,50,000 & 4,00,000 CIDs to be created by Cloud and share with Perf team
  Perf team to inject 150k & 400K CIDs to Performance environment using user injection scripts provided by BE team
  Cloud team to load historical data of 90 days for 150K CID
  Once the historical data is loaded, Cloud team to load Two weeks of data into the system. Provided the dates to update.
Ensure 24hrs ETL process is working fine in Performance environment
Ensure the RDP machine is setup with JMeter and good to execute the performance runs
PT Team to prepare the performance test scripts with all assertions, error handling, transaction controller etc., for all the identified / in-scope scenarios
PT Team to prepare the script / identify the easy way to capture the bearer tokens, Patient ID URLs to form the proper end points and load them the test data file i.e., .csv and configure in JMeter
Once all scripts are completed, PT Team to run the dry run test for 1 hour to ensure all scripts are working fine without any issues and able to achieve the TPS as per the requirement
PT Team to confirm that they are able to access the servers to be monitored from Azure and good for the execution

## Slide 7
S. No. | Application Name | Current Users | Buffer Users | Total Users (Round off) (Current + Buffer Users)
1 | PwD | 22500 | 27450 | 50000
2 | HCP | 1125 | 1125 | 2250
3 | Clinic | 225 | 274 | 500
4 | Most Patients in One Clinic | 1500 | 500 | 2000
5 | Most HCP / Staff in One Clinic | 120 | 80 | 200
User Details (API & ETL)
Total User Details (API only)
Total ETL User process
User Creation – Unique data (Overall)
S. No. | Process Type | No. of hours | Expected Users
1 | ETL | 24 | 50000
S. No. | HCP | PwD | Clinic Admin (Largest Clinic)
1 | 3550 | 50100 | NA
2 | NA | NA | 1 User – 300 Patients, 1 User - 500 Patients, 1 User - 1000 Patients, 1 User – 2000 Patients

## Slide 8
NFRs and In-scope Scenarios
NFRs and In-Scope scenario - Following are the scenarios which will be tested using both API and GUI
Scenario | Duration | Application Name | Transactions per Hour (TPH) | Transactions per Min (TPM) | Transactions per sec (TPS) | Response Time (in sec)
Report generation with 90 & 14, 7 days (Equal Distribution) Scenario - 6d (Best Case) | 1 Hr. | HCP | 6250 | 104 | 1.74 | <20
Insight generation Insights - Schedule Every Sunday at 1am EST | NA | PwD | n/a | n/a | n/a | 4 hours
Navigation (landing page - patient directory) | 1 Hr. | HCP | 828 | 13.80 | 0.23 | <5
Search patient with name to generate the report | 1 Hr. | HCP | 828 | 13.80 | 0.23 | <5
HCP Invite to PwD | 1 Hr. | HCP | 1600 | 26.67 | 0.44 | <5
Staff navigation (Go to staff directory) | 1 Hr. | HCP | 250 | 4.17 | 0.07 | <5
Patient navigation (go to help and click on IFU) | 1 Hr. | HCP | 1000 | 16.70 | 0.28 | <10
Patient navigation (Landing Page OP5 Insights) | 1 Hr. | PwD | 19998 | 333.3 | 5.55 | <5
Select any week | 1 Hr. | PwD | 19998 | 333.3 | 5.56 | <5
After Bolus Highs, click any week |  |  |  |  |  | 
Morning Highs |  |  |  |  |  | 
Afternoon Highs |  |  |  |  |  | 
Evening Highs |  |  |  |  |  | 
Staff Largest Clinics – Single User Test 1 User 300 Patients, 1 User 500 Patients 1 User 1000 Patients, 1 User 2000 Patients | 30 Min | Clinic Admin | 414 | 13.80 | 0.23 | <5
Note: The above response time SLA’s will be compared against with the 95th Percentile as per the standards.

## Slide 9
Overall Execution Summary for API Only
API Test Execution Plan
# | Description | Goals | Type of Test | No. of Cycles | Execution Timelines |  | No. of days
 |  |  |  |  | Start Date | End Date | 
1 | All in-scope scenarios for HCP & PwD (Include - Report Gen scenarios) (Refer slide 8 - NFRs and In-Scope scenarios) Note: Lollipop feature should be available in PF environment before 01/28 (Sprint #1) | Load Test - Achieve targeted users and TPS | Load Test | 2 | 29th Jan 2025 (Sprint #2) | 25th Feb 2025 (Sprint #3) | 20 days
 |  | Scalability Test – HCP worst case scenario to achieve 209 | Scalability Test | 1 |  |  | 
 |  | Identify any memory leaks while during extending duration testing | Endurance Test (24 hours) | 1 |  |  | 
2 | [Option]: If there are any delay in deploying the Lollipop feature into PF environment, Performance team will execute a separate HCP report Gen for 90, 14, 7 days (Equal distribution of report length) – Refer Slide Number: 12 | To Achieve targeted users and TPS | Scalability Test | 2 (One best case TPS One Worst case TPS) | 12th Feb 2025 (Sprint #3) | 25th Feb 2025 (Sprint #3) | 10 days
3 | All in-scope scenarios for HCP & PwD (Include - Report Gen scenarios) Note: Including report preparation + re-execution if there are any failure in the test execution | Stress Test - Identify the breakpoint with 2x and 3x numbers | Stress Test | 2 | 26th Feb 2025 (Sprint #4) | 11th March 2025 (Sprint #4) | 10 Days
4 | 1.5 numbers (150k transaction) test execution with 1.5 code in PF environment DV testing Prep activities | Load Test – Execute load test with 150k transactions in 1.5 code | Load Test | 1 | 12th March 2025 (Sprint #5) | 25th March 2025 (Sprint #5) | 10 days
5 | DV Testing Prep activities (PF2 environment validation, data setup, dry runs | Dry run in PF 2 environment after all setup completed | Dry Run | 1 |  |  | 
5 | DV Testing | Load Test – Achieve the Targeted users and TPS in PF2 environment before go-live | Load Test Dry Run – 1 & Load Test 2 – 400k | 2 3 | 26th March 2025 (Sprint #6) | 8th April 2025 (Sprint #6) | 10 days
Note - Above mentioned timelines are subject to availability of the environment, completion of the scripts, creation of the test data and closure of all pre-requisites.

## Slide 10
10 Users
22 sec
22 sec
22 sec
10 users will ramp up in every 22 sec until user count reaches 407
10 Users
22 sec
10 users will ramp down in every 2 sec until user count reaches 0 Users
10 Users
10 Users
10 Users
22 sec
22 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 407 Users to on the system
Test will run for 1 hour with 407 users
It takes about 15 minutes to ramp up all 407 Users to on the system
Goal#1 – Load Test sample pattern
10 Users
10 Users
User Ramp up Phase
22 sec
API Goals
Goal#1 – All in-scope Scenario include Report Gen (HCP)
The Objective is to ensure that your system will generate accurate, efficient, and reliable report while performing consistently is to meet the agreed response time SLA for all in-scope scenarios with various workloads without any errors or agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Total Duration
1 | Load Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios | 1 | HCP – 324 Users (Total: 9180 Transactions) PwD – 83 Users (Total:20,000 transactions] | 1 Hr.

## Slide 11
Goal#1 – Stress Test (2x) sample pattern
1 hour
3663 Users
10989 Users
32967 Users
Goal#1 – Stress Test (3x) sample pattern
Stress Test Total Duration would be 1 Hrs. (Increase 3x no of users on every 15 Min duration to identify the system / application breakdown point
API Goals
Goal#2 – All in-scope Scenario including Report Gen (HCP)
The Objective is to ensure that your system to identify the breaking point while running all in-scope scenarios with various workloads and capture the % of errors. Also, ensuring that health of the servers should not reach the max threshold limit.
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Total Duration
2 | Stress Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios (2x & 3x Load) | 1 | Increase 2x every 15 Min until system breaks. | 1 Hr.
 |  |  | 1 | Increase 3x every 15 Min until system breaks. | 1 Hr.
1221 Users
1 hour
Stress Test Total Duration would be 1 Hrs. (Increase 2x no of users on every 15 Min duration to identify the system / application breakdown point
1628 Users
3256 Users
6512 Users
814 Users

## Slide 12
Goal#2 – Endurance Test sample pattern
API Goals (Continue…)
Goal#2 – All in-scope Scenario include Report Gen (HCP)
The Objective is to identify potential memory leaks, resource leaks, and any other issues that can cause your system to degrade over time while running the scenarios with various workloads with agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits.
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Total Duration
3 | Endurance Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios | 1 | HCP – 324 Users (Total: 9180 Transactions) PwD – 83 Users (Total:20,000 transactions] | 24 Hrs
CONFIDENTIAL
12
22 sec
10 users will ramp up in every 22 sec until user count reaches 407
10 Users
22 sec
10 users will ramp down in every 22 sec until user count reaches 0 Users
10 Users
10 Users
22 sec
22 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 407 Users to on the system
Test will run for 24 hour with 407 users on a steady state
It takes about 15 minutes to ramp up all 407 Users to on the system
User Ramp up Phase
10 Users
10 Users
10 Users
10 Users
22 sec
22 sec
22 sec
22 sec
10 Users

## Slide 13
API Goals
The Objective is to ensure that your system will generate accurate, efficient, and reliable report while performing consistently is to meet the agreed response time SLA for the report generation scenarios with various workloads without any errors or agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits
# | Test Scenario | HCP / PwD | Test Duration | Transaction per second (TPS) | Transaction per Minute (TPM) | Volume Details | Response Time SLA’s
1 | Scenario 1b+2: 80% of clinics generating equally; 20% generating in chunks - worst case - when they land on the (Report generation of 90, 14, 7 days equal distribution) | HCP | 1 Hr. | 0.22 | 13.13 | 786 | <20 sec
2 | Scenario 3 - HCP Report Generation at the start of the day - first hour (Extending to 30 Min instead of 15 min to see the consistency in the application beyond the expected volume (Report generation of 90, 14, 7 days equal distribution) | HCP | 30 Min | 0.99 | 59.14 | 1774 | <20 sec
3 | Replicate the PwD 6d Scenario (Optional) until PwD execution started. (Report generation of 90, 14, 7 days equal distribution) | HCP | 30 Min | 1.97 | 118.28 | 3548 | <20 sec
4 | Scenario 6a - PwD runs the report in first 15 mins after they get their text message (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 1.39 | 83.33 | 6250 | <20 sec
5 | Scenario 6d - Some PwDs run the report in first 15 mins after they get their Sunday text message at 10am ET – Best Case (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 1.74 | 104.17 | 1563 | <20 sec
6 | Scenario 6d - Some PwDs run the report in first 15 mins after they get their Sunday text message at 10am ET – Worst Case (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 3.48 | 209 | 3135 | <20 sec
Goal#2 HCP & PwD Report Generation

## Slide 14
List of Functionalities
Architectural changes
New Hybrid ETL method
Application Functionalities
Addition of automated basal rates to the reports
Addition of Libre 2 support - completed and deployed to 1.5 FMR
Addition of Manual Basal rate on the reports
IBF processing enhancements
Accommodate users with no CGM data (changing how we calculate reports)
Enhancement to Weekly Insights Calculations
Below are the list of features which are expected to be available, deployed, tested in Performance environment before start of the In-Scope performance test executions.
Out of scope
Any architectural changes, Bug fixing, DB fine tuning, DB profiling, Cloud configuration etc.,
Monitoring of cloud systems
Preparing detailed results for scalability runs is Out of Scope as we follow top-down approach and need to run multiple executions. Only high-level results will be provided
Patient and Staff pending Approve & Deny APIs along with the count scenario.
Any scenarios which are NOT functioning at the time of executions, will be considered out of scope and excluded from the ongoing tests
HA / DR performance testing

## Slide 15
PT Environment Details
Server specifications
# | Resource Name | Azure Service Name | Container count | Resource Group Location | OS | App Service Tier | DB Tier | No. of Servers | Scale instance | LB | No. of VCPUs | Memory allocation (GB) | Region
1 | HCP App Server | app-wus-be-hcp-gibraltar-pf | NA | rg-wus-infra-Gibraltar-pf | Linux | Premium V3 | NA | 1 | 30 | No | 4 | 16 | West US
2 | PWD App Server | app-wus-be-pwd-gibraltar-pf | NA | rg-wus-infra-gibraltar-pf | Linux | Premium V3 (P2V3) | NA | 1 | 30 | No | 4 | 16 | West US
3 | PDF App Services | app-wus-be-pdf-hcp-gibraltar-pf | NA | rg-wus-infra-gibraltar-pf | Linux | Premium V3 (P2V3) | NA | 1 | 30 | No | 4 | 16 | West US
4 | DMS DB | psql-wus-gibraltar-pf | NA | rg-wus-infra-gibraltar-pf | NA | NA | Gen Purpose 4v | 1 |  | No | 4 | 20 (5 GB Per Vcore | West US
5 | Container Group | etl-cloud-api-hcp-pwddatalake-pf | 8 | rg-wus-infra-Gibraltar-pf | NA | NA | NA | 1 |  | No | 4 | 16 | West US
6 |  | etl-cloud-api-hcp-pwddatamart-pf | 10 | rg-wus-infra-Gibraltar-pf | NA | NA | NA | 1 |  | No | 4 | NA | West US

## Slide 16: Thank you!

## Slide 17
In-scope Scenarios with Endpoint URL
In-Scope scenario with Endpoint URL - Following are the scenarios which will be tested using both API and GUI
Sl. No. | Scenario | EndPoint URL
1 | Report generation | /generate?
2 | Navigation (landing page - patient directory) | /patients
3 | Search patient with ID | /patients/device-statistics?
4 | HCP Invite to PwD - Invite Patient (Enter details and click on Invite) | /patients/invitations
5 | Staff navigation (Go to staff directory) | /admin/clinical-workers/approved
6 | Staff navigation (Go to pending staff) | /admin/clinical-workers/pending
7 | Staff navigation (Go to pending patient) | /admin/patients/pending
8 | Staff navigation (Staff Count) - 3 | /admin/users/pending/counts
9 | Patient navigation (goto help and click on IFU ) | 
10 | Patient navigation (Landing Page OP5 Insights) | Profile, dashboard, dashboard/insulin-usage dashboard/insulin-usage/trend, dashboard/summary/glucose-trend, dashboard/summary, learning-material/op5-progress
11 | Select any week | Dashboard, dashboard/insulin-usage, dashboard/insulin-usage/trend dashboard/summary/glucose-trend, dashboard/summary
12 | After Bolus Highs, click any week | patient/insights/${insights}/boluses, patient/insights/${insights}/readings patient/insights/${insights}/modes
13 | Morning Highs | patient/insights/${insights}/boluses patient/insights/${insights}/readings patient/insights/${insights}/modes
14 | Afternoon Highs | patient/insights/${insights}/boluses patient/insights/${insights}/readings patient/insights/${insights}/modes
15 | Evening Highs | patient/insights/${insights}/boluses patient/insights/${insights}/readings patient/insights/${insights}/modes

## Slide 18
Volume Details (API, GUI & ETL)
Total Volume Details (API and GUI)
Total ETL Volume process
User Creation – Unique data (Overall)
S. No. | Process Type | No. of hours | Expected Volume
1 | ETL | 24 | 50000
S. No. | HCP | PwD
1 | 3550 | 50100

## Slide 19
60 sec
50 users will ramp up in every 60 sec until user count reaches 790
50 Users
60 sec
50 users will ramp down in every 60 sec until user count reaches 0 Users
50 Users
50 Users
60 sec
60 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 790 Users to on the system
Test will run for 24 hour to achieve 12,250 volume
It takes about 15 minutes to ramp up all 790 Users to on the system
User Ramp up Phase
50 Users
50 Users
50 Users
50 Users
60 sec
60 sec
60 sec

## Slide 20
Objective & Feature Details
Architecture Diagram
Dependencies
Pre-requisites and Tools
NFRs and In-scope Scenarios
Volume Details (API, GUI & ETL)
Overall Execution Summary for API and GUI
API Goals
  Goal#1 – All in-scope Scenario except report generation
  Goal#2 – HCP & PwD report generation (only)
GUI Goals
  Goal#1 – All in-scope Scenario except Report Generation (PwD)
  Goal#2 – PWD report generation only
  Goal#3 – All in-scope Scenario
List of Functionalities and Out Of Scope
PT Environment Details
Table of Contents

## Slide 21
Objective:
For FMR release execute the below agreed Load tests for HCP and PwD scenarios to understand the overall systems behavior, stability and responsiveness of the API & GUI performance for an application. Also, ensure that per NFR requirements, all the in-scope scenarios for HCP and PwD meet the targeted SLAs, server health is within the threshold limit
1.5 FMR In-scope List of Features:
Objective & Feature Details
Feature Number | Year & Quarter | Type of Feature | Description | Status
INSIGHT-595 | 2024 & Q4 | API | Performance team will discover all the identified workflows (Navigations, search, invitations) in Q3, and prepare API scripts in the available environment | Completed
INSIGHT-476 | 2024 & Q4 | API | Performance Testing preparation for report generation, perform JMeter PoC on setting up the pipeline, setting up the expectations with the cloud team for necessary script preparation | Completed
INSIGHT-477 | 2024 & Q4 | API | All in-scope scenario API scripts to be migrated to PF environment, perform validations, identify test data needs for scripting and execution. Design test scenarios and perform dry run or sanity checks. | In-Progress
INSIGHT-699 | 2024 & Q4 | API | Complete all pre-requisites, prepare and execute API Performance testing on in-scope hcp and pwd applications along with results preparation | In-Progress
INSIGHT-723 | 2024 & Q4 | GUI | Performance team will be creating GUI scripts in PF environment for all the in-scope scenarios and validate the same. | To-Do
INSIGHT-715 | 2025 & Q1 | GUI | Performance team will be executing all in-scope scenarios based on the Data Model volume numbers along with the types of scenarios. | To-Do

## Slide 22
Overall Execution Summary for API and GUI
API Test Execution Plan
# | Description | Goals | Type of Test | No. of Cycles | Execution Timelines |  | No. of days
 |  |  |  |  | Start Date | End Date | 
1 | All in-scope scenarios for HCP & PwD except Report Generation scenarios. (Refer slide 8 - NFRs and In-Scope scenarios) (Including re-execution timelines) | Load Test - Achieve targeted users and TPS Stress Test - Identify the breakpoint | Load Test Stress Test | Load Test – 1 Stress Test – 1 Load Test – 1 (Re-test) | 23rd Dec 2024 | 10th Jan 2025 | 13 days
2 | Generate report for 90, 14, 7 days (Equal distribution of report length) for HCP and PwD scenarios. Note: Lollipop feature needs to be deployed in PF environment | To Achieve targeted users and TPS | Load Test | 6 | 13th Jan 2025 | 3rd Feb 2025 | 14 days
3 | All in-scope scenarios for HCP & PwD | Identify any memory leaks while during extending duration testing | Endurance Test (24 hours) | 1 | 10th Feb 2025 | 14th Feb 2025 | 5 days
GUI Test Execution Plan – Planned during 1.6 release (March)
# | Description | Goals | Type of Test | No. of Cycles | Execution Timelines |  | No. of days
 |  |  |  |  | Start Date | End Date | 
1 | All in-scope scenarios for HCP & PwD (Refer slide 8 - NFRs and In-Scope scenarios) Note: Generate report with equal distribution (Including re-execution timelines) | Load Test - Achieve targeted users and TPS Stress Test - Identify the breakpoint | Load Test Stress Test Scalability | Load Test – 1 Stress Test – 1 Scalability Test - 3 | TBD | TBD | TBD
1 | Generate report for 90, 14, 7 days (Equal distribution of report length) for HCP and PwD scenarios. | To identify max no. of concurrent users | Scalability | 8 | TBD | TBD | TBD
3 | All in-scope scenarios for HCP & PwD (Refer slide 8 - NFRs and In-Scope scenarios) Note: Generate report with equal distribution | Sustainability of user's responsiveness and consistency in the TPS | Endurance Test (Optional) | 1 | TBD | TBD | TBD
Note - Above mentioned timelines are subject to availability of the environment, completion of the scripts, creation of the test data and closure of all pre-requisites.

## Slide 23
NFRs and In-scope Scenarios
NFRs and In-Scope scenario - Following are the scenarios which will be tested using both API and GUI
Scenario | Duration | Application Name | Transactions per Hour (TPH) | Transactions per Min (TPM) | Transactions per sec (TPS) | Response Time (in sec)
Report generation with 90 & 14, 7 days | 1 Hr. | HCP | 1774 | 59.14 | 0.99 | <20
Report generation with 90 & 14 days | 1 Hr. | PwD | 3,135 | 209 | 3.48 | <20
Insight generation Insights - Schedule Every Sunday at 1am EST | NA | PwD | n/a | n/a | n/a | 4 hours
Navigation (landing page - patient directory) | 1 Hr. | HCP | 828 | 13.80 | 0.23 | <5
Search patient with name to generate the report | 1 Hr. | HCP | 828 | 13.80 | 0.23 | <5
HCP Invite to PwD | 1 Hr. | HCP | 1600 | 26.67 | 0.44 | <5
Staff navigation (Go to staff directory) | 1 Hr. | HCP | 250 | 4.17 | 0.07 | <5
Staff navigation (Go to pending staff) | 1 Hr. | HCP | 250 | 4.17 | 0.07 | <5
Staff navigation (Go to pending patient) | 1 Hr. | HCP | 250 | 4.17 | 0.07 | <5
Patient navigation (go to help and click on IFU) | 1hr. | HCP | 500 | 16.70 | 0.28 | <5
Patient navigation (Landing Page OP5 Insights) | 30 Min | PwD | 9999 | 333.3 | 5.56 | <5
Select any week |  |  |  |  |  | 
After Bolus Highs, click any week |  |  |  |  |  | 
Morning Highs |  |  |  |  |  | 
Afternoon Highs |  |  |  |  |  | 
Evening Highs |  |  |  |  |  | 
Staff Largest Clinics – Single User Test | 30 Min | Clinic Admin | 1 User 300 Patients 1 User 500 Patients 1 User 1000 Patients 1 User 2000 Patients | NA | NA | <5
Note: The above response time SLA’s will be compared against with the 95th Percentile as per the standards.

## Slide 24
Overall Execution Summary for API and GUI
API Test Execution Plan
# | Description | Goals | Type of Test | No. of Cycles | Execution Timelines |  | No. of days
 |  |  |  |  | Start Date | End Date | 
1 | All in-scope scenarios for HCP & PwD (Include - Report Gen scenarios) (Refer slide 8 - NFRs and In-Scope scenarios) Note: Lollipop feature should be available in PF environment before 01/28 (Sprint #1) | Load Test - Achieve targeted users and TPS Stress Test - Identify the breakpoint Note: P | Load Test Stress Test | Two Load Tests Two StressTests Post fixes: One Load Test | 23rd Dec 2024 | 10th Jan 2025 | 13 days
2 | Option 2: If delay in deploying the Lollipop feature into PF environment, Performance team will execute separate HCP report Gen for 90, 14, 7 days (Equal distribution of report length) | To Achieve targeted users and TPS | Load Test | 2 | 13th Jan 2025 | 3rd Feb 2025 | 14 days
3 | All in-scope scenarios for HCP & PwD | Identify any memory leaks while during extending duration testing | Endurance Test (24 hours) | 1 | 10th Feb 2025 | 14th Feb 2025 | 5 days
GUI Test Execution Plan – Planned during 1.6 release (March)
# | Description | Goals | Type of Test | No. of Cycles | Execution Timelines |  | No. of days
 |  |  |  |  | Start Date | End Date | 
1 | All in-scope scenarios for HCP & PwD (Refer slide 8 - NFRs and In-Scope scenarios) Note: Generate report with equal distribution (Including re-execution timelines) | Load Test - Achieve targeted users and TPS Stress Test - Identify the breakpoint | Load Test Stress Test Scalability | Load Test – 1 Stress Test – 1 Scalability Test - 3 | TBD | TBD | TBD
1 | Generate report for 90, 14, 7 days (Equal distribution of report length) for HCP and PwD scenarios. | To identify max no. of concurrent users | Scalability | 8 | TBD | TBD | TBD
3 | All in-scope scenarios for HCP & PwD (Refer slide 8 - NFRs and In-Scope scenarios) Note: Generate report with equal distribution | Sustainability of user's responsiveness and consistency in the TPS | Endurance Test (Optional) | 1 | TBD | TBD | TBD
Note - Above mentioned timelines are subject to availability of the environment, completion of the scripts, creation of the test data and closure of all pre-requisites.

## Slide 25
API Goals
The Objective is to ensure that your system will generate accurate, efficient, and reliable report while performing consistently is to meet the agreed response time SLA for the report generation scenarios with various workloads without any errors or agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits
# | Test Scenario | HCP / PwD | Test Duration | Transaction per second (TPS) | Transaction per Minute (TPM) | Volume Details | Response Time SLA’s
1 | Scenario 1b+2: 80% of clinics generating equally; 20% generating in chunks - worst case - when they land on the (Report generation of 90, 14, 7 days equal distribution) | HCP | 1 Hr. | 0.22 | 13.13 | 786 | <20 sec
2 | Scenario 3 - HCP Report Generation at the start of the day - first hour (Extending to 30 Min instead of 15 min to see the consistency in the application beyond the expected volume (Report generation of 90, 14, 7 days equal distribution) | HCP | 30 Min | 0.99 | 59.14 | 1774 | <20 sec
3 | Replicate the PwD 6d Scenario (Optional) until PwD execution started. (Report generation of 90, 14, 7 days equal distribution) | HCP | 30 Min | 1.97 | 118.28 | 3548 | <20 sec
4 | Scenario 6a - PwD runs the report in first 15 mins after they get their text message (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 1.39 | 83.33 | 1250 | <20 sec
5 | Scenario 6d - Some PwDs run the report in first 15 mins after they get their Sunday text message at 10am ET – Best Case (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 1.74 | 104.17 | 1563 | <20 sec
6 | Scenario 6d - Some PwDs run the report in first 15 mins after they get their Sunday text message at 10am ET – Worst Case (Report generation of 90, 14, 7 days equal distribution) | PwD | 15 Min | 3.48 | 209 | 3135 | <20 sec
Goal#2 HCP & PwD Report Generation

## Slide 26
50 Users
60 sec
60 sec
60 sec
50 users will ramp up in every 60 sec until user count reaches 790
50 Users
60 sec
50 users will ramp down in every 60 sec until user count reaches 0 Users
50 Users
50 Users
50 Users
60 sec
60 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 790 Users to on the system
Test will run for 1 hour to achieve 24,500 volume
It takes about 15 minutes to ramp up all 790 Users to on the system
Goal#1 – Load Test sample pattern
1 hour
50 Users
50 Users
User Ramp up Phase
60 sec
29,000 Volume
58,000 Volume
1,26,000Volume
Goal#1 – Stress Test sample pattern
Stress Test Total Duration would be 2 Hrs. (Increase 2x no of users on every 30 Min duration to identify the system / application breakdown point
GUI Goals
Goal#1 – All in-scope Scenario except Report generation
The Objective is to ensure that your system will generate accurate, efficient, and reliable report while performing consistently is to meet the agreed response time SLA for all in-scope scenarios with various workloads without any errors or agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits
24,500 volume
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Duration
1 | Load Test – 1 | All in-scope scenarios | 1 | HCP – 4,500 & PwD – 20,000 (Total:24,500] | 1.5 Hr.
2 | Load Test -2 | All scenarios except report generation 90, 14 and 7 days | 1 | HCP – 4,500 & PwD – 20,000 (Total:24,500] | 1.5 Hr.
3 | Stress Test – 1 | All scenarios except report generation 90 days 2x every 30 min | 1 | 24,500 * 1x = 24,500 Increase 2x every 30 Min until system breaks. | 2 Hr.
4 | Scalability Test - 1 | All scenarios except report generation 90 days. Benchmark the no. of users until identify the breaking point | 3 | HCP – 4,500 & PwD – 20,000 = 24,500 Note – Numbers to be adjusted based on 1st test | 1 Hr.

## Slide 27
Goal#1 – Endurance Test sample pattern
GUI Goals (Continue…)
Goal#1 – All in-scope Scenario except Report generation
The Objective is to identify potential memory leaks, resource leaks, and any other issues that can cause your system to degrade over time while running the scenarios with various workloads with agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits.
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Total Duration
6 | Endurance Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios | 1 | HCP – 4,500 (1 Hr.) PwD – 20,000 (30 Min) ([Total:24,500] Average volume: 12.250 | 24 Hrs
CONFIDENTIAL
27
60 sec
50 users will ramp up in every 60 sec until user count reaches 790
50 Users
60 sec
50 users will ramp down in every 60 sec until user count reaches 0 Users
50 Users
50 Users
60 sec
60 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 790 Users to on the system
Test will run for 24 hour to achieve 12,250 volume
It takes about 15 minutes to ramp up all 790 Users to on the system
User Ramp up Phase
50 Users
50 Users
50 Users
50 Users
60 sec
60 sec
60 sec
60 sec
50 Users

## Slide 28
Goal#2 – GUI based performance testing with user base using PWD report generation only
Scalability test is to measures performance of a system when the number of user requests are scaled up or down.
GUI Goals
# | Scenario | Type of Test | Volume Details
1 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 1 | 50,000
2 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 2 | 40,000
3 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 3 | 30,000
4 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 4 | 20,000
5 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 5 | 10,000
6 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 6 | 5,000
7 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 7 | 1,000
8 | Report generation with 90-, 14- and 7-days report with users' equal distribution | Scalability Test 8 | 500
Chart: GUI Goal#1 - PwD Report Generation
| Scalability Test 1 | Scalability Test 2 | Scalability Test 3 | Scalability Test 4 | Scalability Test 5 | Scalability Test 6 | Scalability Test 7 | Scalability Test 8
Total No. of Users | 50000 | 40000 | 30000 | 20000 | 10000 | 5000 | 1000 | 500
Login as OP5 user
2
3
Home Page
1
4
5
Logout
Navigate to Menu and select Download Physician Report
PwD
PWD NAVIGATION FLOW
90, 14 & 7 days
Notes: Ok but Remove sheet and add new slide with all list of scenarios, move to appendix

## Slide 29
10 Users
22 sec
22 sec
22 sec
10 users will ramp up in every 22 sec until user count reaches 407
10 Users
22 sec
10 users will ramp down in every 2 sec until user count reaches 0 Users
10 Users
10 Users
10 Users
22 sec
22 sec
Steady State
User Ramp Down Phase
It takes about 15 minutes to ramp up all 407 Users to on the system
Test will run for 1 hour with 407 users
It takes about 15 minutes to ramp up all 407 Users to on the system
Goal#1 – Load Test sample pattern
1 hour
10 Users
10 Users
User Ramp up Phase
22 sec
1420 Users
2840 Users
5680 Users
Goal#1 – Stress Test sample pattern
Stress Test Total Duration would be 2 Hrs. (Increase 2x no of users on every 30 Min duration to identify the system / application breakdown point
API Goals
Goal#1 – All in-scope Scenario except Report generation
The Objective is to ensure that your system will generate accurate, efficient, and reliable report while performing consistently is to meet the agreed response time SLA for all in-scope scenarios with various workloads without any errors or agreed % of errors. Also, ensuring that health of the servers should be in good condition or within the threshold limits
# | Type of Test | Scenario Details | No. of Cycles | Volume Details | Total Duration
1 | Load Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios | 1 | HCP – 355 Users (Total: 9180 Transactions) PwD – 83 Users (Total:20,000 transactions] | 1 Hr.
2 | Stress Test | All scenarios which are listed on the above table NFRs and In-Scope scenarios (2x Load) | 1 | 24,500 * 1x = 24,500 Increase 2x every 30 Min until system breaks. | 2 Hrs.
710 Users